## Summary
QC Triage — Executive Summary
AI Finance Forum · analysis date 29 Jul 2026 · 62 QC findings + 31 manual tests
Difficulty clusters
Cluster | Count | Estimate
Easy | 24 | 2–3 days
Medium | 31 | 2–3 weeks
Hard | 10 | 4–6 weeks
Done | 3 | — (already done / closed)
Total work items | 68 | QC-049 counted once (Easy).
Feature status (before any coding)
State | Items
Already exists — verify only | QC-049, QC-062
Closed — not a defect | QC-050, QC-045
Partially exists — finish it | QC-053, QC-054, QC-055, QC-056, QC-059
Not built at all | QC-035, QC-043, QC-044, QC-051, QC-052, QC-057, QC-058, QC-060, QC-061
Code exists but still wrong | QC-006, QC-015, QC-020, QC-032, QC-039
The 8 "Critical" findings, re-read
Finding | Verdict | Why
QC-049 | Already DONE | Explanation panel is already coded.
QC-050 | CLOSED | Guided story mode — not a defect.
QC-006 | EASY | Just clear 190 test conversations.
QC-001–QC-005 | ONE root | All five trace to a split dataset + hand-typed impact text.
⇒ The eight "Critical" items are really 2 work packages, not 8.
Do this before touching any code
1. Redeploy the latest build to Azure and re-run sheet 02B. The tracker tested the 28-Jul Azure build, but the repo is already ahead — several "Open" findings are already coded and will simply drop.
2. Chase Dataset_AI_Finance_Forum_v1.xlsx. This replacement dataset (referenced by sheet 04) is missing from the repo and blocks the 4 heaviest findings (QC-002, QC-003, QC-043, QC-044). Without it, the Hard cluster cannot start.
Key takeaway
The headline number (62 findings) overstates the work. Two features are already built, two are closed, and the eight "Critical" items collapse into two packages. Redeploy and retest first, knock out the Easy cluster (MT-018 crash first), then attack the two computed-number packages that a CFO is most likely to catch on stage — before spending weeks on the dataset re-architecture.

## Triage Detail
QC Triage — AI Finance Forum · Item-level detail
62 QC findings + manual-test items, triaged by difficulty. Source: QC_Testing_Tracker_AI_Finance_Forum_v2.0_20260728.xlsx. Verified by reading code on local repo main@76b3231 (not a running-app test). Analysis date: 29 Jul 2026.
ID | Finding / Feature | Feature status | Difficulty | Group | Phase | Notes / How to fix
MT-018 | Cross-agent scenario crashes: "Object of type Decimal is not JSON serializable" | Still broken | Easy | - | 1 | Crash bug — do this first. Coerce Decimal→float in the serializer. It kills the flagship cross-agent scenario, which is the main selling point of the demo.
QC-039 | Remove the word "illustrative" from the dashboards | Still broken | Easy | - | 1 | Delete the string in 8 locations. Leave the instance in the prompt config — that is an instruction to the LLM, not UI text.
QC-006 | Clear 190 test conversations / unfiltered /conversations endpoint | Still broken | Easy | - | 1 | DELETE the rows, or add a filter to the /conversations query.
QC-041 | Alert titled "W5" while the data is "W6" | Needs fix | Easy | - | 1 | Template variable swapped.
QC-009 | Two different EBITDA-margin targets shown | Needs fix | Easy | - | 1 | Change the hardcoded 15% → 15.7%.
QC-013 | Bar labelled "Current 95%" | Needs fix | Easy | - | 1 | Rename to "95% for all", or align the assumption to 7,557.5.
QC-014 | KPI says 22 flags but the table shows 10 rows | Needs fix | Easy | - | 1 | Add a caption "showing 10 of 22".
QC-018 | Top-2 overdue-share label | Needs fix | Easy | - | 1 | Rename the label.
QC-025 | FX-exposure label | Needs fix | Easy | - | 1 | Rename the label and invert the display logic.
QC-030 | "Overdue AR" label used for only 2 customers | Needs fix | Easy | - | 1 | Rename the label.
QC-031 | Annual figure shown against a per-cycle one | Needs fix | Easy | - | 1 | Add an "(annualized)" label.
QC-032 | 900 mn shown under 3 different names | Still broken | Easy | - | 1 | Unify the naming.
QC-012 | Two near-identical numbers (-1,880 vs -1,881) | Needs fix | Easy | - | 1 | Differentiate them by rounding or label.
QC-027 | Margin truncated instead of rounded | Needs fix | Easy | - | 1 | truncate → round half up.
QC-028 | DSO gauge shows 120% progress | Needs fix | Easy | - | 1 | Flip the gauge direction.
QC-029 | Inconsistent number formatting | Needs fix | Easy | - | 1 | One shared formatter helper, used everywhere.
QC-033 | Chart-pair ordering is reversed | Needs fix | Easy | - | 1 | Align the config order.
QC-034 | Zero-height bar sitting beside a valued bar | Needs fix | Easy | - | 1 | Change the chart type or add an explicit label.
QC-036 | Side chart duplicates the main chart | Needs fix | Easy | - | 1 | Change the side-slot content.
QC-038 | Bucket column dumps everything into the oldest bucket | Needs fix | Easy | - | 1 | Rename the column to "Oldest bucket".
QC-024 | Leakage opens on an empty chart | Needs fix | Easy | - | 1 | Change default_view (workaround; the true root cause is QC-001).
QC-042 | Starter prompts are all single-agent | Needs fix | Easy | - | 1 | Add 2 cross-agent prompts in the config JSON.
QC-049 | Formula-explanation (Reasoning) panel | Already exists | Easy | - | Done | Already coded (infoRegistry.js, InfoCard.jsx, openInfo()). Only verify the ~40 entries are complete.
QC-059 | Global reset button | Partially exists | Easy | - | 1 | Slider reset already works; add a one-click global reset (view + simulator + chat) using the existing endpoint.
QC-004 | Payment deferral moves headroom the wrong way | Needs fix | Medium | A | 2 | Group A shares one root: the impact text is typed by hand in the spec. Fix once — build an evaluator that derives impact from forecast/baseline, then render from it. Do 004/005/016/017/019 as ONE package.
QC-005 | Headroom mixed up with cash balance | Needs fix | Medium | A | 2 | Same root as Group A — computed-impact evaluator.
QC-016 | DSO impact does not match its recommendation | Needs fix | Medium | A | 2 | Same root as Group A.
QC-017 | Combined action only partly computed | Needs fix | Medium | A | 2 | Same root as Group A.
QC-019 | Credit line keyed to the wrong week | Needs fix | Medium | A | 2 | Same root as Group A.
QC-007 | High-risk KPI (2,500) vs tier chart (5,000) | Needs fix | Medium | B | 2 | Group B: one number, one meaning.
QC-008 | "Top 5" has 3 different definitions | Needs fix | Medium | B | 2 | Standardize a single definition.
QC-011 | COGS variance shown as 2,930 vs 1,880 | Needs fix | Medium | B | 2 | Reconcile to one figure.
QC-015 | Split invoice 1,950 sits outside the 7,845 total | Still broken | Medium | B | 2 | Leakage baseline is hardcoded (overbill_amount=400, other_blocked=500, at_risk=7845).
QC-040 | Forecast before/after customer deferral is unclear | Needs fix | Medium | B | 2 | Make the two states explicit.
QC-001 | Leakage category chart returns all zeros | Needs fix | Medium | C | 3 | Amount column not mapped for import batch 17. Difficulty is medium, but it is sequenced inside the Phase-3 dependency chain.
QC-020 | Agent-name key inconsistent across endpoints | Still broken | Medium | C | 4 | Registry uses finance.collection but the payload uses "collections".
QC-021 | 47 action cards are duplicative | Needs fix | Medium | C | 4 | Trim to 3–5 per agent.
QC-023 | 47 alerts really tell ~8 stories | Needs fix | Medium | C | 4 | De-duplicate.
QC-026 | Recovery rate ignores receivable age | Needs fix | Medium | C | 4 | Fold ageing into the calculation.
QC-046 | Vendor score = flag count × 20 | Needs fix | Medium | C | 4 | Ignores amount and severity; reweight the score.
QC-048 | Mockup and app show different numbers | Needs fix | Medium | C | 4 | Reconcile the two.
QC-035 | Period label on every chart | Not built | Medium | D | 4 | Add a period/as_of field to the payload and render it in the titles.
QC-051 | Save / load / compare scenarios | Not built | Medium | D | 4 | Needs a new table + UI.
QC-052 | Simulator presets | Not built | Medium | D | 4 | 3–4 named presets per agent.
QC-053 | Scope selector | Partially exists | Medium | D | 4 | Pattern already exists in Finance (scope_options); replicate to the 3 other agents.
QC-054 | KPI sparkline | Partially exists | Medium | D | 4 | KpiSparkline component exists; Finance, Leakage and Collection still need to emit trend.
QC-055 | Action confidence level | Partially exists | Medium | D | 4 | confidence_label column exists in the DB; expose it in service/router/UI.
QC-056 | Execution-chain animation | Partially exists | Medium | D | 4 | RouteRenderer already renders routes; add the staged execution trace.
QC-057 | Agent activity feed | Not built | Medium | D | 4 | New endpoint + panel, separate from alerts (the bell currently shows alerts, not activity).
QC-061 | Next-best-action cards on the dashboard | Not built | Medium | D | 4 | Action data exists; render it in Workboard.
MT-010 | DSO lands at 53.5 (should reset clean to 57.36) | Needs fix | Medium | E | 4 | Reset logic.
MT-014 | Approve cannot be undone | Needs fix | Medium | E | 4 | Add an undo.
MT-015 | Agent Action missing from Action History; simulation_summary null | Needs fix | Medium | E | 4 | Persist the action and its summary.
MT-023 | Response is slow (>8 seconds) | Needs fix | Medium | E | 4 | Performance work.
MT-025 | Export/download feature missing | Not built | Medium | E | 4 | Add export.
QC-002 | Four agents sit on unrelated batches (19 / 17 / 11 / 2) | Needs fix | Hard | - | 3 | Root cause of almost every number problem. Needs a single ledger + re-seed + repointing all 4 agents.
QC-003 | Collection revenue base is 15× Finance | Needs fix | Hard | - | 3 | Derivative of QC-002 — cannot be fixed on its own.
QC-044 | Data volume far below what was requested | Not built | Hard | - | 3 | Needs new dimensions (legal_entity, store, item, category) that are not in the schema at all. Migration + ETL of 25,588 sales / 2,016 AR / 630 AP rows.
QC-043 | 22 filters missing | Not built | Hard | - | 3 | Fully depends on QC-044; touches every endpoint and every UI component.
QC-047 | Treasury levers not wired to the Collection ledger | Needs fix | Hard | - | 4 | Needs a shared cross-agent simulation model. This is the key demo differentiator — keep it a priority.
QC-022 | Action impacts stack with no double-count guard | Needs fix | Hard | - | 4 | Needs portfolio netting — a new mathematical model.
QC-010 | Price variance ~10× smaller than claimed | Needs fix | Hard | - | 4 | Reconcile to the base model; unclear which figure is correct.
QC-037 | Cash chart cannot explain why W5 is low | Not built | Hard | - | Deferred | Needs 288 cash-line rows (only a balance series exists). Depends on the replacement dataset.
QC-058 | Indonesian language switcher | Not built | Hard | - | Deferred | Full i18n: UI strings + payload + LLM output. The prompt currently locks "responses in English only".
QC-060 | Compute with the CFO's own parameters | Not built | Hard | - | Deferred | Needs a chat↔simulator bridge plus a calculation-step viewer.
QC-062 | Chat renders charts + tables | Already exists | Done | - | Done | html_renderer.py emits chart+table, rendered by BlockRenderer.jsx → ChartRenderer.jsx.
QC-050 | Guided story mode | Closed | Done | - | Done | Closed as "Not a defect" — not worked on.
QC-045 | Interactive behaviour untested | Closed | Done | - | Done | Not an application defect; already executed via sheet 02B.

## Feature Status
Feature status detail — what already exists vs what is missing
Already exists — verify only (no coding)
ID | Feature | Evidence in code
QC-049 | Formula-explanation (Reasoning) panel | infoRegistry.js (415 lines, 1:1 port of mockup v9.4) + InfoCard.jsx + openInfo() in Workboard.jsx
QC-062 | Chat shows charts + tables | html_renderer.py emits chart+table → BlockRenderer.jsx → ChartRenderer.jsx
QC-050 | Guided story mode | Closed as "Not a defect"
QC-045 | Interactive behaviour untested | Not an app defect; executed via sheet 02B
Partially exists — foundation done, finish it
ID | What already exists | What is still missing
QC-054 | KpiSparkline component + Treasury emits trend | Finance, Leakage and Collection do not emit trend yet
QC-053 | Finance has scope_options ["all","fx"] + scope state | The 3 other agents have no scope_options
QC-055 | confidence_label column exists in the DB | Not exposed in actions/service.py, router.py or the UI
QC-056 | RouteRenderer.jsx renders the route list | Static — no animation / staged execution trace
QC-059 | Slider reset works (MT-008 passed) | No single-click global reset (view + simulator + chat)
Not built at all
ID | Feature | Note
QC-043 | Filters (22 of them) | No filter parameter anywhere in any endpoint
QC-044 | Dataset volume | No legal_entity / store / item / category table or column in models.py
QC-035 | Period label on charts | No period / as_of field in any dashboard payload
QC-051 | Save / load / compare scenarios | Only 4 recalculate endpoints, no persistence
QC-052 | Simulator presets | Simulator payload is only inputs + baseline
QC-057 | Agent activity feed | The bell shows alerts (findings), not agent activity
QC-058 | Indonesian language switcher | No i18n; prompt locks "responses in English only"
QC-060 | Compute with your own parameters | Chat and recalculate are not connected
QC-061 | Next-best-action cards on dashboard | Workboard renders no actions at all
Code exists but is still wrong
ID | Problem | Location
QC-039 | "illustrative" still scattered | finance/leakage/treasury dashboard files
QC-020 | Agent key clashes | registry finance.collection vs payload "collections"
QC-015 / 032 | Leakage baseline hardcoded | overbill_amount=400, other_blocked=500, at_risk=7845
QC-006 | /conversations returns all history unfiltered | finance_agents_html.py:414

## Work Sequence
Recommended work order — by impact / effort, not by QC number
Phase | Timing | What to do | Why / gate closed
Phase 0 | ~1 day | 1) Deploy the latest build to Azure and re-run sheet 02B; strike findings that are already resolved. 2) Chase Dataset_AI_Finance_Forum_v1.xlsx. | Some findings drop for free. Without the dataset the Hard cluster cannot begin.
Phase 1 | 2–3 days | The whole Easy cluster (24 items). MT-018 (Decimal JSON crash) FIRST. | Closes gates #4, #5 and part of #6, #7 on sheet 06B.
Phase 2 | ~1 week | Group A (impact text computed, not typed) + Group B (one number, one meaning). | Closes gate #3 and gate #6 — the ones a CFO is most likely to catch on stage, at a fraction of the Hard-cluster cost.
Phase 3 | 3–4 weeks | QC-044 → QC-002 → QC-003 → QC-001 → QC-043, strictly in that order. | A mandatory dependency chain — reversing the order means doing the work twice.
Phase 4 | after Phase 3 | Remaining Group D features, then QC-047 and QC-022 (plus the rest of Group C/E and QC-010). | QC-047 (cross-agent simulation) is the demo's real differentiator — keep it a priority.
Deferred | after the demo | QC-058 (i18n), QC-060 (own-parameter compute), QC-037. | Expensive and do not block the 4-minute demo story.